## Sheet1
IED - ENGR 2050 |  | Project - Smart Lighting System | [16 empty] | Team - SightRPI
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [8 empty] | Week 4 | [6 empty] | Week 5
[21 empty] | MS1 Presentation |  | Memo | [11 empty] | Demo |  | MS2 Presentation | Final Report
Task # | Task | Status | Owner(s) | Start | End | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S
1 | Interview with Professor Connor | 100% | A,C | 2017-05-30 | 2017-05-30
2 | Research emergencies in homes | 100% | A,C | 2017-05-30 | 2017-05-30
3 | Benchmark other products on the market | 100% | Z1,A | 2017-05-30 | 2017-05-31
4 | Decide between camera or smart lighting method | 100% | ALL | 2017-05-31 | 2017-05-31
5 | Determine main functions of device | 100% | ALL | 2017-05-31 | 2017-05-31
6 | Assign subsystems to group members | 100% | ALL | 2017-05-31 | 2017-05-31
7 | Borrow & Purchase necessary hardware | 100% | Z2 | 2017-06-01 | 2017-06-02
8 | Determine tech specifications | 100% | A | 2017-06-01 | 2017-06-04
9 | Write network communication module | 100% | C | 2017-06-01 | 2017-06-09
10 | Write memo | 100% | ALL | 2017-06-01 | 2017-06-10
11 | Slides for presentation 1 | 100% | ALL | 2017-06-01 | 2017-06-11
12 | Write iPhone App | 100% | Z1 | 2017-06-01 | 2017-06-19
13 | Write functional programs | 100% | D | 2017-06-01 | 2017-06-20
14 | Slides for presentation 2 | 100% | ALL | 2017-06-01 | 2017-06-25
15 | Build circuits | 100% | Z2 | 2017-06-03 | 2017-06-11
16 | Build model (for presentation 2) | 100% | A,Z2 | 2017-06-05 | 2017-06-16
17 | Write iPhone communication module | 100% | C | 2017-06-10 | 2017-06-19
18 | Practice presentation 1 | 100% | ALL | 2017-06-11 | 2017-06-12
19 | Build data Structure | 100% | D | 2017-06-12 | 2017-06-16
20 | Install circuits and model | 100% | A,Z2 | 2017-06-17 | 2017-06-18
21 | Collect data | 100% | Z2,D | 2017-06-17 | 2017-06-23
22 | Write final report | 100% | ALL | 2017-06-17 | 2017-06-28
23 | Test wireless module | 100% | C | 2017-06-18 | 2017-06-21
24 | iPhone App Test | 100% | Z1 | 2017-06-18 | 2017-06-23
25 | Test Hardware | 100% | A,Z2 | 2017-06-19 | 2017-06-20
26 | Test functional programs | 100% | D | 2017-06-21 | 2017-06-25
27 | Test final model | 100% | ALL | 2017-06-23 | 2017-06-26
28 | Practice presentation 2 | 100% | ALL | 2017-06-25 | 2017-06-26
Alex | A
Cornelius | C
Ding | D
Ziyi | Z1
Zhen | Z2
Everyone | ALL